## Workflow
Task ID | Task Description | Status | Estimated Start time | Estimated end time | Actual start time | Actual end time
Story-1_Workflow | To create new, modify or delete the workflows | Defined | 17th-Feb
Story-2_Nested Workflow | To create nested workflows | New
Story-3_Conditional worfklow |  | New

## Sheet1
Task ID | Task Description | Status | Estimated Start time | Estimated end time | Actual start time | Actual end time
T-001 | Functionality to create workflow on html page | Completed
T-002 | Functionality to modify workflow on html page | Completed
T-003 | Functionality to delete workflow on html page | Completed
T-004 | Sorting of shapes based on shape ID in ascending order | Completed
T-005 | Storing the workflows in the database | Completed
T-006 | Database redesigining | In Progress | 2020-01-21 | 2020-01-23 | 2020-01-21 | 2020-01-23
T-007 | Poiniting of the cursor where new shape is added | Completed | 2020-01-21 | 2020-01-23 | 2020-01-21 | 2020-01-23
T-008 | Support of HTML Tag | In Progress | 2020-01-21 | 2020-01-23 | 2020-01-21 | 2020-01-23
T-009 | Support of Nested workflow upto 3 levels | In Progress | 2020-01-27 | 2nd-Feb | 2020-01-27 | 2020-02-03
T-010 | Support of Nested workflow upto 10 levels | New | 2020-02-03
T-011 | Support of conditional loops | In Progress
T-012 | Functionality to add workflows against user | Defined
T-013 | Functionality to create an admin user who can view, add, modify any workflow even created by other users
T-014 | Funtionality to provide view, add, modify , delete access to users
T-015 | Creation of executable of the project
T-016 | Support to upload word document
T-017 | Reading the word document and displaying the workflows on html
T-018 | Creating Junits
T-019 | Creating one executable file